## Sheet1
Sno. | SHOT NAME | TASK | STATUS | THUMBNAIL | DEPARTMENT | ARTIST | Version | START DATE | ETA | NOTES
1 | RL_01_ADD_SH_0090 | Villain Body touchup | WIP |  |  | Sunny Walunj | prep_v003 | 2024-10-10 | 2024-10-29
2 | RL_01_ADD_SH_0100 | Villain Body touchup | WIP |  |  | Sunny Walunj | prep_v003 | 2024-10-10 | 2024-10-28
3 | RL_01_ADD_SH_0110 | Villain Body touchup | WIP |  |  | Sunny Walunj | prep_v003 | 2024-10-10 | 2024-10-29
4 | RL_01_ADD_SH_0120 | Villain Body touchup | WIP |  |  | Sunny Walunj | prep_v002 | 2024-10-10 | 2024-10-29
5 | RL_01_ADD_SH_0130 | Villain Body touchup | WIP |  |  | Nikhil Shivshive | prep_v002 | 2024-10-10 | 2024-10-29
6 | RL_01_ADD_SH_0140 | Villain Body touchup | WIP |  |  | Nikhil Shivshive | prep_v004 | 2024-10-10 | 2024-10-29
7 | RL_01_ADD_SH_0150 | Villain Body touchup | WIP |  |  | Nikhil Shivshive | comp_v001 | 2024-10-10 | 2024-10-29
8 | RL_01_ADD_SH_0160 | Villain Body touchup | WIP |  |  | Prasad Kothawade | prep_v006 | 2024-10-10 | 2024-10-30
9 | RL_01_SH_0330 | Recently Done | Approved |  |  |  |  | 2024-10-10
10 | RL_01_SH_0350 | Recently Done | Approved |  |  |  |  | 2024-10-10
11 | RL_01_SH_0360 | Recently Done | Approved |  |  |  |  | 2024-10-10
12 | RL_01_SH_0380 | Recently Done | Approved |  |  |  |  | 2024-10-10
13 | RL_01_SH_0390 | Recently Done | Approved |  |  |  |  | 2024-10-10
14 | RL_01_SH_0400 | Recently Done | Approved |  |  |  |  | 2024-10-10
15 | RL_02_ADD_SH_0210 | Hairs reveal | Approved |  |  | Vivek Mahajan | comp_v005 | 2024-10-10 | 2024-10-26
16 | RL_02_ADD_SH_0220 | Neck Wrinkles | Approved |  |  | Vivek Mahajan | comp_v007 | 2024-10-10 | 2024-10-25
17 | RL_02_ADD_SH_0240 | Neck Wrinkles & Double chin | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-10-25
18 | RL_02_ADD_SH_0260 | Neck Wrinkles | Approved |  |  | Vivek Mahajan | comp_v004 | 2024-10-10 | 2024-10-26
19 | RL_02_ADD_SH_0270 | Hand | Approved |  |  | Vivek Mahajan | comp_v001 | 2024-10-10 | 2024-10-26
20 | RL_02_ADD_SH_0280 | Neck Wrinkles | Approved |  |  | Vivek Mahajan | comp_v007 | 2024-10-10 | 2024-10-25
21 | RL_02_ADD_SH_0300 | Neck Wrinkles | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-10-26
22 | RL_02_ADD_SH_0320 | Neck Wrinkles | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-10-26
23 | RL_02_ADD_SH_0380 | Neck Wrinkles | Kickback |  |  | Vivek Mahajan | comp_v002 | 2024-10-10 | 2024-10-29
24 | RL_02_ADD_SH_0390 | Hand | Kickback |  |  | Vivek Mahajan | comp_v002 | 2024-10-10 | 2024-10-26
25 | RL_02_ADD_SH_0400 | Neck Wrinkles | Kickback |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-10-26
26 | RL_02_ADD_SH_0470 | Fix the makeup | Kickback |  |  | Prasad Kothawade | comp_v007 | 2024-10-10 | 2024-10-29
27 | RL_02_ADD_SH_0510 | Hand & Wrinkles | Approved |  |  | Prasad Kothawade | comp_v008 | 2024-10-10 | 2024-10-25
28 | RL_02_ADD_SH_0520 | Wrinkles | Approved |  |  | Prasad Kothawade | comp_v009 | 2024-10-10 | 2024-10-25
29 | RL_02_SH_0130 | Body | Approved |  |  | Shraddha Anawat | comp_007 | 2024-10-10 | 2024-10-24
30 | RL_02_SH_0500 | Body | Approved |  |  | Shraddha Anawat | comp_v005 | 2024-10-10 | 2024-10-24
31 | RL_03_ADD_SH_0020 | Hand | Approved |  |  | Shraddha Anawat | comp_v009 | 2024-10-10 | 2024-10-25
32 | RL_03_ADD_SH_0040 | Hand | Approved |  |  | Shraddha Anawat | comp_v002 | 2024-10-10 | 2024-10-25
33 | RL_03_ADD_SH_0060 | Hand | Approved |  |  | Shraddha Anawat | comp_v002 | 2024-10-10 | 2024-10-25
34 | RL_03_ADD_SH_0080 | Hand | Approved |  |  | Shraddha Anawat | comp_v001 | 2024-10-10 | 2024-10-26
35 | RL_03_ADD_SH_0100 | Hand | Approved |  |  | Shraddha Anawat | comp_v005 | 2024-10-10 | 2024-10-26
36 | RL_03_ADD_SH_0120 | Hand | Approved |  |  | Shraddha Anawat | comp_v003 | 2024-10-10 | 2024-10-26
37 | RL_03_ADD_SH_0160 | Hand | Approved |  |  | Shraddha Anawat | comp_v003 | 2024-10-10 | 2024-10-26
38 | RL_03_ADD_SH_0180 | CC Issue | Approved |  |  | Shraddha Anawat | comp_v002 | 2024-10-10 | 2024-10-26
39 | RL_03_ADD_SH_0250 | Hand | Approved |  |  | Shraddha Anawat | comp_v003 | 2024-10-10 | 2024-10-27
40 | RL_03_ADD_SH_0260 | Day Light prep | WIP |  |  | Shraddha Anawat |  | 2024-10-10 | 2024-11-07
41 | RL_03_ADD_SH_0270 | Day Light prep | Approved |  |  | Om Atawane | comp_v003 | 2024-10-10 | 2024-10-28
42 | RL_03_ADD_SH_0280 | Day Light prep | Approved |  |  | Om Atawane | comp_v002 | 2024-10-10 | 2024-11-06
43 | RL_03_ADD_SH_0290 | Hand & Check crop line | Approved |  |  | Sunny Walunj | prep_v004 | 2024-10-10 | 2024-10-24
44 | RL_03_ADD_SH_0300 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-24
45 | RL_03_ADD_SH_0310 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-24
46 | RL_03_ADD_SH_0320 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-25
47 | RL_03_ADD_SH_0330 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-25
48 | RL_03_ADD_SH_0340 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v004 | 2024-10-10 | 2024-10-25
49 | RL_03_ADD_SH_0350 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-25
50 | RL_03_ADD_SH_0360 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-25
51 | RL_03_ADD_SH_0370 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-25
52 | RL_03_ADD_SH_0380 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v001 | 2024-10-10 | 2024-10-25
53 | RL_03_ADD_SH_0390 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-25
54 | RL_03_ADD_SH_0400 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-25
55 | RL_03_ADD_SH_0410 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-26
56 | RL_03_ADD_SH_0420 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v003 | 2024-10-10 | 2024-10-26
57 | RL_03_ADD_SH_0430 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v003 | 2024-10-10 | 2024-10-26
58 | RL_03_ADD_SH_0440 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-26
59 | RL_03_ADD_SH_0450 | Day Light prep | Approved |  |  | Shraddha Anawat | comp_v002 | 2024-10-10 | 2024-11-06
60 | RL_03_ADD_SH_0460 | Day Light prep | Approved |  |  | Om Atawane | comp_v003 | 2024-10-10 | 2024-10-28
61 | RL_03_ADD_SH_0470 | Hand & Check crop line | Approved |  |  | Sunny Walunj | prep_v001 | 2024-10-10 | 2024-10-26
62 | RL_03_ADD_SH_0480 | Day Light prep | Approved |  |  | Om Atawane | comp_v005 | 2024-10-10 | 2024-10-26
63 | RL_03_ADD_SH_0490 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v003 | 2024-10-10 | 2024-10-26
64 | RL_03_ADD_SH_0500 | Hand & Check crop line | Approved |  |  | Sunny Walunj | prep_v002 | 2024-10-10 | 2024-10-26
65 | RL_03_ADD_SH_0510 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v006 | 2024-10-10 | 2024-10-25
66 | RL_03_ADD_SH_0520 | Hand & Check crop line | Approved |  |  | Sunny Walunj | prep_v002 | 2024-10-10 | 2024-10-26
67 | RL_03_SH_0480 | Body | Approved |  |  | Shraddha Anawat | prep_v003 | 2024-10-10 | 2024-10-27
68 | RL_03_SH_0500 | Body | Approved |  |  | Shraddha Anawat | prep_v002 | 2024-10-10 | 2024-10-28
69 | RL_03_SH_0510 | Body | Approved |  |  | Shraddha Anawat | comp_v003 | 2024-10-10 | 2024-10-28
70 | RL_03_SH_0680_L02 | Body | Approved |  |  | Kiran Lachure | prep_v001 | 2024-10-10 | 2024-10-29
71 | RL_03_SH_0690 | Body | Approved |  |  | Kiran Lachure | prep_v003 | 2024-10-10 | 2024-10-30
72 | RL_03_SH_0710 | Body | Approved |  |  | Kiran Lachure | prep_v002 | 2024-10-10 | 2024-10-30
73 | RL_03_SH_0730 | Body | Approved |  |  | Kiran Lachure | prep_v003 | 2024-10-10 | 2024-10-28
74 | RL_03_SH_0740 | Body | Approved |  |  | Shraddha Anawat | prep_v002 | 2024-10-10 | 2024-10-29
75 | RL_03_SH_0750 | Body | Approved |  |  | Kiran Lachure | prep_v002 | 2024-10-10 | 2024-10-29
76 | RL_03_SH_0760 | Body | Approved |  |  | Shraddha Anawat | prep_v002 | 2024-10-10 | 2024-10-28
77 | RL_03_SH_0770 | Body | Approved |  |  | Shraddha Anawat | prep_v002 | 2024-10-10 | 2024-10-29
78 | RL_03_SH_0780 | Body | Approved |  |  | Shraddha Anawat | prep_v003 | 2024-10-10 | 2024-11-06
79 | RL_03_SH_0790 | Body | Approved |  |  | Shraddha Anawat | prep_v002 | 2024-10-10 | 2024-10-30
80 | RL_03_SH_0860 | Body | Approved |  |  | Shraddha Anawat | prep_v002 | 2024-10-10 | 2024-10-29
81 | RL_03_SH_0920_L02 | Body & Face | Approved |  |  | Nikhil Shivshive | comp_v003 | 2024-10-10 | 2024-10-24
82 | RL_03_SH_0940 | Body | Approved |  |  | Nikhil Shivshive | comp_v003 | 2024-10-10 | 2024-10-25
83 | RL_03_SH_0950_L02 | Body | Approved |  |  | Nikhil Shivshive | comp_v006 | 2024-10-10 | 2024-10-29
84 | RL_04_ADD_SH_0030 | Face got too soft & Neck | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-26
85 | RL_04_ADD_SH_0040 | Face got too soft & Neck | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-26
86 | RL_04_ADD_SH_0050 | Face got too soft & Neck | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-26
87 | RL_04_ADD_SH_0060 | Face got too soft & Neck | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-26
88 | RL_04_ADD_SH_0061 | Face got too soft & Neck & Shrap Edge on hand | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-26
89 | RL_04_ADD_SH_0070 | Face got too soft & Neck | Approved |  |  | Nikhil Shivshive | comp_v001 | 2024-10-10 | 2024-10-26
90 | RL_04_ADD_SH_0080 | Face got too soft & Neck | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-26
91 | RL_04_ADD_SH_0090 | Face got too soft & Neck double Chin | Approved |  |  | Nikhil Shivshive | comp_v005 | 2024-10-10 | 2024-10-27
92 | RL_04_ADD_SH_0180 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v004 | 2024-10-10 | 2024-10-27
93 | RL_04_ADD_SH_0190 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v002 | 2024-10-10 | 2024-10-26
94 | RL_04_ADD_SH_0200 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v002 | 2024-10-10 | 2024-10-26
95 | RL_04_ADD_SH_0210 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v005 | 2024-10-10 | 2024-10-28
96 | RL_04_ADD_SH_0220 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v002 | 2024-10-10 | 2024-10-26
97 | RL_04_ADD_SH_0230 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v003 | 2024-10-10 | 2024-10-27
98 | RL_04_ADD_SH_0240 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v005 | 2024-10-10 | 2024-10-29
99 | RL_04_ADD_SH_0250 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-28
100 | RL_04_ADD_SH_0260 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v004 | 2024-10-10 | 2024-10-29
101 | RL_04_ADD_SH_0270 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v006 | 2024-10-10 | 2024-10-30
102 | RL_04_ADD_SH_0280 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v002 | 2024-10-10 | 2024-10-30
103 | RL_04_ADD_SH_0330 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v005 | 2024-10-10 | 2024-10-29
104 | RL_04_ADD_SH_0340 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v005 | 2024-10-10 | 2024-10-29
105 | RL_04_ADD_SH_0350 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v004 | 2024-10-10 | 2024-10-28
106 | RL_04_ADD_SH_0360 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v005 | 2024-10-10 | 2024-10-28
107 | RL_04_ADD_SH_0370 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-28
108 | RL_04_ADD_SH_0380 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v004 | 2024-10-10 | 2024-10-28
109 | RL_04_ADD_SH_0390 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v003 | 2024-10-10 | 2024-10-28
110 | RL_04_ADD_SH_0400 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v004 | 2024-10-10 | 2024-10-29
111 | RL_04_ADD_SH_0410 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v004 | 2024-10-10 | 2024-10-29
112 | RL_04_ADD_SH_0420 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v004 | 2024-10-10 | 2024-10-29
113 | RL_04_ADD_SH_0700 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_v006 | 2024-10-10 | 2024-10-27
114 | RL_04_ADD_SH_0710 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_v004 | 2024-10-10 | 2024-10-27
115 | RL_04_ADD_SH_0720 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_v003 | 2024-10-10 | 2024-10-27
116 | RL_04_ADD_SH_0730 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_v004 | 2024-10-10 | 2024-10-27
117 | RL_04_ADD_SH_0740 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_v004 | 2024-10-10 | 2024-10-27
118 | RL_04_ADD_SH_0750 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_v005 | 2024-10-10 | 2024-10-27
119 | RL_04_ADD_SH_0760 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-27
120 | RL_04_ADD_SH_0770 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_v003 | 2024-10-10 | 2024-10-27
121 | RL_04_ADD_SH_0780 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_002 | 2024-10-10 | 2024-10-27
122 | RL_04_ADD_SH_0900 | Body | Approved |  |  | Om Atawane | comp_v003 | 2024-10-10 | 2024-10-28
123 | RL_04_ADD_SH_0910 | Body | Approved |  |  | Om Atawane | comp_v003 | 2024-10-10 | 2024-10-28
124 | RL_04_ADD_SH_0920 | Body | Approved |  |  | Om Atawane | comp_v002 | 2024-10-10 | 2024-10-28
125 | RL_04_ADD_SH_0930 | Body | Approved |  |  | Om Atawane | comp_v002 | 2024-10-10 | 2024-10-28
126 | RL_04_ADD_SH_0940 | Body | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-11-06
127 | RL_04_ADD_SH_0950 | Body | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-29
128 | RL_04_ADD_SH_0960 | Body | Approved |  |  | Sunny Walunj | comp_v004 | 2024-10-10 | 2024-11-06
129 | RL_04_ADD_SH_0970 | Body | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-11-06
130 | RL_04_ADD_SH_1150 | Body | Approved |  |  | Vivek Mahajan | comp_v005 | 2024-10-10 | 2024-10-27
131 | RL_04_ADD_SH_1160 | Body | Approved |  |  | Vivek Mahajan | comp_v004 | 2024-10-10 | 2024-10-27
132 | RL_04_ADD_SH_1170 | Body | Approved |  |  | Vivek Mahajan | comp_v007 | 2024-10-10 | 2024-11-06
133 | RL_04_ADD_SH_1200 | Hand | Approved |  |  | Vivek Mahajan | comp_v002 | 2024-10-10 | 2024-10-28
134 | RL_04_ADD_SH_1240 | Hand | Approved |  |  | Vivek Mahajan | comp_v002 | 2024-10-10 | 2024-11-06
135 | RL_04_ADD_SH_1260 | Hand | Approved |  |  | Vivek Mahajan | comp_v004 | 2024-10-10 | 2024-11-06
136 | RL_04_ADD_SH_1270 | Hand | Approved |  |  | Vivek Mahajan | comp_v005 | 2024-10-10 | 2024-10-28
137 | RL_04_ADD_SH_1290 | Hand | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-10-28
138 | RL_04_ADD_SH_1350 | Hand | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-10-29
139 | RL_04_ADD_SH_1380 | Hand | Approved |  |  | Vivek Mahajan | comp_v004 | 2024-10-10 | 2024-10-29
140 | RL_04_ADD_SH_1420 | Hand | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-11-06
141 | RL_04_ADD_SH_1440 | Hand | Approved |  |  | Vivek Mahajan | comp_v004 | 2024-10-10 | 2024-10-29
142 | RL_04_ADD_SH_1480 | Hand | Approved |  |  | Vivek Mahajan | comp_v004 | 2024-10-10 | 2024-11-06
143 | RL_04_ADD_SH_1500 | Hand | Approved |  |  | Vivek Mahajan | comp_v002 | 2024-10-10 | 2024-11-06
144 | RL_04_ADD_SH_1540 | Hand | Approved |  |  | Vivek Mahajan | comp_v004 | 2024-10-10 | 2024-11-06
145 | RL_04_ADD_SH_1560 | Hand | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-11-06
146 | RL_04_ADD_SH_1580 | Hand | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-11-06
147 | RL_04_ADD_SH_1590 | Hand | Approved |  |  | Vivek Mahajan | comp_v005 | 2024-10-10 | 2024-11-06
148 | RL_04_ADD_SH_1610 | Hand | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-11-06
149 | RL_04_SH_0180 | Need to render comp version after replacing prep | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-25
150 | RL_04_SH_0190 | Body | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-25
151 | RL_04_SH_0200 | Need to render comp version after replacing prep | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-25
152 | RL_04_SH_0210 | Need to render comp version after replacing prep | Approved |  |  | Nikhil Shivshive | comp_v003 | 2024-10-10 | 2024-10-25
153 | RL_04_SH_0220 | Need to render comp version after replacing prep | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-25
154 | RL_04_SH_0230 | Need to render comp version after replacing prep | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-25
155 | RL_04_SH_0280 | Need to render again with the updated prep version | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-10-24
156 | RL_04_SH_0480 | Body | Approved |  |  | Shraddha Anawat | comp_v009 | 2024-10-10 | 2024-10-25
157 | RL_04_SH_0490 | Body | Approved |  |  | Shraddha Anawat | comp_v003 | 2024-10-10 | 2024-10-25
158 | RL_04_SH_0500 | Body | Approved |  |  | Shraddha Anawat | comp_v005 | 2024-10-10 | 2024-10-25
159 | RL_04_SH_0510 | Body | Approved |  |  | Shraddha Anawat | comp_v006 | 2024-10-10 | 2024-10-25
160 | RL_04_SH_0690 | Body | Approved |  |  | Vivek Mahajan | comp_v006 | 2024-10-10 | 2024-11-06
161 | RL_04_SH_0710 | Body | Approved |  |  | Vivek Mahajan | comp_v005 | 2024-10-10 | 2024-11-06
162 | RL_04_SH_0820 | Face & Body | Approved |  |  | Vivek Mahajan | comp_v002 | 2024-10-10 | 2024-10-28
163 | RL_04_SH_0840 | Face & Body | Approved |  |  | Vivek Mahajan | comp_v002 | 2024-10-10 | 2024-10-28
164 | RL_05_ADD_SH_0120 | Under eyes | Approved |  |  | Kiran Lachure | comp_v002 | 2024-10-10 | 2024-10-25
165 | RL_05_ADD_SH_0140 | Hand | Approved |  |  | Kiran Lachure | comp_v002 | 2024-10-10 | 2024-10-24
166 | RL_05_ADD_SH_0200 | Makeup & Chest | Approved |  |  | Kiran Lachure | comp_v003 | 2024-10-10 | 2024-10-25
167 | RL_05_ADD_SH_0240 | Sharp Forhead and Remove Wrinkles | Approved |  |  | Kiran Lachure | comp_v003 | 2024-10-10 | 2024-10-25
168 | RL_05_ADD_SH_0260 | Neck Wrinkles | Approved |  |  | Kiran Lachure | comp_002 | 2024-10-10 | 2024-10-26
169 | RL_05_ADD_SH_0280 | Neck Wrinkles | Approved |  |  | Kiran Lachure | comp_v002 | 2024-10-10 | 2024-10-26
170 | RL_05_ADD_SH_0290 | Neck Wrinkles | Approved |  |  | Kiran Lachure | comp_v002 | 2024-10-10 | 2024-10-26
171 | RL_05_ADD_SH_0400 | Legs | Approved |  |  | Kiran Lachure | comp_v005 | 2024-10-10 | 2024-10-27
172 | RL_05_ADD_SH_0420 | Reduce Chest | Approved |  |  | Kiran Lachure | comp_v002 | 2024-10-10 | 2024-10-27
173 | RL_05_ADD_SH_0510 | Legs | Approved |  |  | Kiran Lachure | comp_v002 | 2024-10-10 | 2024-10-26
174 | RL_05_ADD_SH_0550 | Face & blackspot | Approved |  |  | Kiran Lachure | comp_v003 | 2024-10-10 | 2024-10-27
175 | RL_05_ADD_SH_0660 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-27
176 | RL_05_ADD_SH_0700 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-27
177 | RL_05_ADD_SH_0740 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-27
178 | RL_05_ADD_SH_0820 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-27
179 | RL_05_ADD_SH_0840 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-27
180 | RL_05_ADD_SH_0860 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-27
181 | RL_05_ADD_SH_0880 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-27
182 | RL_05_ADD_SH_0900 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-27