## Sheet1
| Sno. | SHOT NAME | TASK | STATUS | THUMBNAIL | DEPARTMENT | ARTIST | Version | START DATE | ETA | NOTES
0 | 1 | RL_01_ADD_SH_0090 | Villain Body touchup | WIP |  |  | Sunny Walunj | prep_v003 | 2024-10-10 | 2024-10-29
1 | 2 | RL_01_ADD_SH_0100 | Villain Body touchup | WIP |  |  | Sunny Walunj | prep_v003 | 2024-10-10 | 2024-10-28
2 | 3 | RL_01_ADD_SH_0110 | Villain Body touchup | WIP |  |  | Sunny Walunj | prep_v003 | 2024-10-10 | 2024-10-29
3 | 4 | RL_01_ADD_SH_0120 | Villain Body touchup | WIP |  |  | Sunny Walunj | prep_v002 | 2024-10-10 | 2024-10-29
4 | 5 | RL_01_ADD_SH_0130 | Villain Body touchup | WIP |  |  | Nikhil Shivshive | prep_v002 | 2024-10-10 | 2024-10-29
5 | 6 | RL_01_ADD_SH_0140 | Villain Body touchup | WIP |  |  | Nikhil Shivshive | prep_v004 | 2024-10-10 | 2024-10-29
6 | 7 | RL_01_ADD_SH_0150 | Villain Body touchup | WIP |  |  | Nikhil Shivshive | comp_v001 | 2024-10-10 | 2024-10-29
7 | 8 | RL_01_ADD_SH_0160 | Villain Body touchup | WIP |  |  | Prasad Kothawade | prep_v006 | 2024-10-10 | 2024-10-30
8 | 9 | RL_01_SH_0330 | Recently Done | Approved |  |  |  |  | 2024-10-10
9 | 10 | RL_01_SH_0350 | Recently Done | Approved |  |  |  |  | 2024-10-10
10 | 11 | RL_01_SH_0360 | Recently Done | Approved |  |  |  |  | 2024-10-10
11 | 12 | RL_01_SH_0380 | Recently Done | Approved |  |  |  |  | 2024-10-10
12 | 13 | RL_01_SH_0390 | Recently Done | Approved |  |  |  |  | 2024-10-10
13 | 14 | RL_01_SH_0400 | Recently Done | Approved |  |  |  |  | 2024-10-10
14 | 15 | RL_02_ADD_SH_0210 | Hairs reveal | Approved |  |  | Vivek Mahajan | comp_v005 | 2024-10-10 | 2024-10-26
15 | 16 | RL_02_ADD_SH_0220 | Neck Wrinkles | Approved |  |  | Vivek Mahajan | comp_v007 | 2024-10-10 | 2024-10-25
16 | 17 | RL_02_ADD_SH_0240 | Neck Wrinkles & Double chin | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-10-25
17 | 18 | RL_02_ADD_SH_0260 | Neck Wrinkles | Approved |  |  | Vivek Mahajan | comp_v004 | 2024-10-10 | 2024-10-26
18 | 19 | RL_02_ADD_SH_0270 | Hand | Approved |  |  | Vivek Mahajan | comp_v001 | 2024-10-10 | 2024-10-26
19 | 20 | RL_02_ADD_SH_0280 | Neck Wrinkles | Approved |  |  | Vivek Mahajan | comp_v007 | 2024-10-10 | 2024-10-25
20 | 21 | RL_02_ADD_SH_0300 | Neck Wrinkles | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-10-26
21 | 22 | RL_02_ADD_SH_0320 | Neck Wrinkles | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-10-26
22 | 23 | RL_02_ADD_SH_0380 | Neck Wrinkles | Kickback |  |  | Vivek Mahajan | comp_v002 | 2024-10-10 | 2024-10-29
23 | 24 | RL_02_ADD_SH_0390 | Hand | Kickback |  |  | Vivek Mahajan | comp_v002 | 2024-10-10 | 2024-10-26
24 | 25 | RL_02_ADD_SH_0400 | Neck Wrinkles | Kickback |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-10-26
25 | 26 | RL_02_ADD_SH_0470 | Fix the makeup | Kickback |  |  | Prasad Kothawade | comp_v007 | 2024-10-10 | 2024-10-29
26 | 27 | RL_02_ADD_SH_0510 | Hand & Wrinkles | Approved |  |  | Prasad Kothawade | comp_v008 | 2024-10-10 | 2024-10-25
27 | 28 | RL_02_ADD_SH_0520 | Wrinkles | Approved |  |  | Prasad Kothawade | comp_v009 | 2024-10-10 | 2024-10-25
28 | 29 | RL_02_SH_0130 | Body | Approved |  |  | Shraddha Anawat | comp_007 | 2024-10-10 | 2024-10-24
29 | 30 | RL_02_SH_0500 | Body | Approved |  |  | Shraddha Anawat | comp_v005 | 2024-10-10 | 2024-10-24
30 | 31 | RL_03_ADD_SH_0020 | Hand | Approved |  |  | Shraddha Anawat | comp_v009 | 2024-10-10 | 2024-10-25
31 | 32 | RL_03_ADD_SH_0040 | Hand | Approved |  |  | Shraddha Anawat | comp_v002 | 2024-10-10 | 2024-10-25
32 | 33 | RL_03_ADD_SH_0060 | Hand | Approved |  |  | Shraddha Anawat | comp_v002 | 2024-10-10 | 2024-10-25
33 | 34 | RL_03_ADD_SH_0080 | Hand | Approved |  |  | Shraddha Anawat | comp_v001 | 2024-10-10 | 2024-10-26
34 | 35 | RL_03_ADD_SH_0100 | Hand | Approved |  |  | Shraddha Anawat | comp_v005 | 2024-10-10 | 2024-10-26
35 | 36 | RL_03_ADD_SH_0120 | Hand | Approved |  |  | Shraddha Anawat | comp_v003 | 2024-10-10 | 2024-10-26
36 | 37 | RL_03_ADD_SH_0160 | Hand | Approved |  |  | Shraddha Anawat | comp_v003 | 2024-10-10 | 2024-10-26
37 | 38 | RL_03_ADD_SH_0180 | CC Issue | Approved |  |  | Shraddha Anawat | comp_v002 | 2024-10-10 | 2024-10-26
38 | 39 | RL_03_ADD_SH_0250 | Hand | Approved |  |  | Shraddha Anawat | comp_v003 | 2024-10-10 | 2024-10-27
39 | 40 | RL_03_ADD_SH_0260 | Day Light prep | WIP |  |  | Shraddha Anawat |  | 2024-10-10 | 2024-11-07
40 | 41 | RL_03_ADD_SH_0270 | Day Light prep | Approved |  |  | Om Atawane | comp_v003 | 2024-10-10 | 2024-10-28
41 | 42 | RL_03_ADD_SH_0280 | Day Light prep | Approved |  |  | Om Atawane | comp_v002 | 2024-10-10 | 2024-11-06
42 | 43 | RL_03_ADD_SH_0290 | Hand & Check crop line | Approved |  |  | Sunny Walunj | prep_v004 | 2024-10-10 | 2024-10-24
43 | 44 | RL_03_ADD_SH_0300 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-24
44 | 45 | RL_03_ADD_SH_0310 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-24
45 | 46 | RL_03_ADD_SH_0320 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-25
46 | 47 | RL_03_ADD_SH_0330 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-25
47 | 48 | RL_03_ADD_SH_0340 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v004 | 2024-10-10 | 2024-10-25
48 | 49 | RL_03_ADD_SH_0350 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-25
49 | 50 | RL_03_ADD_SH_0360 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-25
50 | 51 | RL_03_ADD_SH_0370 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-25
51 | 52 | RL_03_ADD_SH_0380 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v001 | 2024-10-10 | 2024-10-25
52 | 53 | RL_03_ADD_SH_0390 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-25
53 | 54 | RL_03_ADD_SH_0400 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-25
54 | 55 | RL_03_ADD_SH_0410 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-26
55 | 56 | RL_03_ADD_SH_0420 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v003 | 2024-10-10 | 2024-10-26
56 | 57 | RL_03_ADD_SH_0430 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v003 | 2024-10-10 | 2024-10-26
57 | 58 | RL_03_ADD_SH_0440 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-26
58 | 59 | RL_03_ADD_SH_0450 | Day Light prep | Approved |  |  | Shraddha Anawat | comp_v002 | 2024-10-10 | 2024-11-06
59 | 60 | RL_03_ADD_SH_0460 | Day Light prep | Approved |  |  | Om Atawane | comp_v003 | 2024-10-10 | 2024-10-28
60 | 61 | RL_03_ADD_SH_0470 | Hand & Check crop line | Approved |  |  | Sunny Walunj | prep_v001 | 2024-10-10 | 2024-10-26
61 | 62 | RL_03_ADD_SH_0480 | Day Light prep | Approved |  |  | Om Atawane | comp_v005 | 2024-10-10 | 2024-10-26
62 | 63 | RL_03_ADD_SH_0490 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v003 | 2024-10-10 | 2024-10-26
63 | 64 | RL_03_ADD_SH_0500 | Hand & Check crop line | Approved |  |  | Sunny Walunj | prep_v002 | 2024-10-10 | 2024-10-26
64 | 65 | RL_03_ADD_SH_0510 | Hand & Check crop line | Approved |  |  | Sunny Walunj | comp_v006 | 2024-10-10 | 2024-10-25
65 | 66 | RL_03_ADD_SH_0520 | Hand & Check crop line | Approved |  |  | Sunny Walunj | prep_v002 | 2024-10-10 | 2024-10-26
66 | 67 | RL_03_SH_0480 | Body | Approved |  |  | Shraddha Anawat | prep_v003 | 2024-10-10 | 2024-10-27
67 | 68 | RL_03_SH_0500 | Body | Approved |  |  | Shraddha Anawat | prep_v002 | 2024-10-10 | 2024-10-28
68 | 69 | RL_03_SH_0510 | Body | Approved |  |  | Shraddha Anawat | comp_v003 | 2024-10-10 | 2024-10-28
69 | 70 | RL_03_SH_0680_L02 | Body | Approved |  |  | Kiran Lachure | prep_v001 | 2024-10-10 | 2024-10-29
70 | 71 | RL_03_SH_0690 | Body | Approved |  |  | Kiran Lachure | prep_v003 | 2024-10-10 | 2024-10-30
71 | 72 | RL_03_SH_0710 | Body | Approved |  |  | Kiran Lachure | prep_v002 | 2024-10-10 | 2024-10-30
72 | 73 | RL_03_SH_0730 | Body | Approved |  |  | Kiran Lachure | prep_v003 | 2024-10-10 | 2024-10-28
73 | 74 | RL_03_SH_0740 | Body | Approved |  |  | Shraddha Anawat | prep_v002 | 2024-10-10 | 2024-10-29
74 | 75 | RL_03_SH_0750 | Body | Approved |  |  | Kiran Lachure | prep_v002 | 2024-10-10 | 2024-10-29
75 | 76 | RL_03_SH_0760 | Body | Approved |  |  | Shraddha Anawat | prep_v002 | 2024-10-10 | 2024-10-28
76 | 77 | RL_03_SH_0770 | Body | Approved |  |  | Shraddha Anawat | prep_v002 | 2024-10-10 | 2024-10-29
77 | 78 | RL_03_SH_0780 | Body | Approved |  |  | Shraddha Anawat | prep_v003 | 2024-10-10 | 2024-11-06
78 | 79 | RL_03_SH_0790 | Body | Approved |  |  | Shraddha Anawat | prep_v002 | 2024-10-10 | 2024-10-30
79 | 80 | RL_03_SH_0860 | Body | Approved |  |  | Shraddha Anawat | prep_v002 | 2024-10-10 | 2024-10-29
80 | 81 | RL_03_SH_0920_L02 | Body & Face | Approved |  |  | Nikhil Shivshive | comp_v003 | 2024-10-10 | 2024-10-24
81 | 82 | RL_03_SH_0940 | Body | Approved |  |  | Nikhil Shivshive | comp_v003 | 2024-10-10 | 2024-10-25
82 | 83 | RL_03_SH_0950_L02 | Body | Approved |  |  | Nikhil Shivshive | comp_v006 | 2024-10-10 | 2024-10-29
83 | 84 | RL_04_ADD_SH_0030 | Face got too soft & Neck | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-26
84 | 85 | RL_04_ADD_SH_0040 | Face got too soft & Neck | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-26
85 | 86 | RL_04_ADD_SH_0050 | Face got too soft & Neck | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-26
86 | 87 | RL_04_ADD_SH_0060 | Face got too soft & Neck | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-26
87 | 88 | RL_04_ADD_SH_0061 | Face got too soft & Neck & Shrap Edge on hand | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-26
88 | 89 | RL_04_ADD_SH_0070 | Face got too soft & Neck | Approved |  |  | Nikhil Shivshive | comp_v001 | 2024-10-10 | 2024-10-26
89 | 90 | RL_04_ADD_SH_0080 | Face got too soft & Neck | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-26
90 | 91 | RL_04_ADD_SH_0090 | Face got too soft & Neck double Chin | Approved |  |  | Nikhil Shivshive | comp_v005 | 2024-10-10 | 2024-10-27
91 | 92 | RL_04_ADD_SH_0180 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v004 | 2024-10-10 | 2024-10-27
92 | 93 | RL_04_ADD_SH_0190 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v002 | 2024-10-10 | 2024-10-26
93 | 94 | RL_04_ADD_SH_0200 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v002 | 2024-10-10 | 2024-10-26
94 | 95 | RL_04_ADD_SH_0210 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v005 | 2024-10-10 | 2024-10-28
95 | 96 | RL_04_ADD_SH_0220 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v002 | 2024-10-10 | 2024-10-26
96 | 97 | RL_04_ADD_SH_0230 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v003 | 2024-10-10 | 2024-10-27
97 | 98 | RL_04_ADD_SH_0240 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v005 | 2024-10-10 | 2024-10-29
98 | 99 | RL_04_ADD_SH_0250 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-28
99 | 100 | RL_04_ADD_SH_0260 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v004 | 2024-10-10 | 2024-10-29
100 | 101 | RL_04_ADD_SH_0270 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v006 | 2024-10-10 | 2024-10-30
101 | 102 | RL_04_ADD_SH_0280 | Neck Wrinkles | Approved |  |  | Prasad Kothawade | comp_v002 | 2024-10-10 | 2024-10-30
102 | 103 | RL_04_ADD_SH_0330 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v005 | 2024-10-10 | 2024-10-29
103 | 104 | RL_04_ADD_SH_0340 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v005 | 2024-10-10 | 2024-10-29
104 | 105 | RL_04_ADD_SH_0350 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v004 | 2024-10-10 | 2024-10-28
105 | 106 | RL_04_ADD_SH_0360 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v005 | 2024-10-10 | 2024-10-28
106 | 107 | RL_04_ADD_SH_0370 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-28
107 | 108 | RL_04_ADD_SH_0380 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v004 | 2024-10-10 | 2024-10-28
108 | 109 | RL_04_ADD_SH_0390 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v003 | 2024-10-10 | 2024-10-28
109 | 110 | RL_04_ADD_SH_0400 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v004 | 2024-10-10 | 2024-10-29
110 | 111 | RL_04_ADD_SH_0410 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v004 | 2024-10-10 | 2024-10-29
111 | 112 | RL_04_ADD_SH_0420 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v004 | 2024-10-10 | 2024-10-29
112 | 113 | RL_04_ADD_SH_0700 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_v006 | 2024-10-10 | 2024-10-27
113 | 114 | RL_04_ADD_SH_0710 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_v004 | 2024-10-10 | 2024-10-27
114 | 115 | RL_04_ADD_SH_0720 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_v003 | 2024-10-10 | 2024-10-27
115 | 116 | RL_04_ADD_SH_0730 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_v004 | 2024-10-10 | 2024-10-27
116 | 117 | RL_04_ADD_SH_0740 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_v004 | 2024-10-10 | 2024-10-27
117 | 118 | RL_04_ADD_SH_0750 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_v005 | 2024-10-10 | 2024-10-27
118 | 119 | RL_04_ADD_SH_0760 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-27
119 | 120 | RL_04_ADD_SH_0770 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_v003 | 2024-10-10 | 2024-10-27
120 | 121 | RL_04_ADD_SH_0780 | Neck Wrinkles | Approved |  |  | Sunny Walunj | comp_002 | 2024-10-10 | 2024-10-27
121 | 122 | RL_04_ADD_SH_0900 | Body | Approved |  |  | Om Atawane | comp_v003 | 2024-10-10 | 2024-10-28
122 | 123 | RL_04_ADD_SH_0910 | Body | Approved |  |  | Om Atawane | comp_v003 | 2024-10-10 | 2024-10-28
123 | 124 | RL_04_ADD_SH_0920 | Body | Approved |  |  | Om Atawane | comp_v002 | 2024-10-10 | 2024-10-28
124 | 125 | RL_04_ADD_SH_0930 | Body | Approved |  |  | Om Atawane | comp_v002 | 2024-10-10 | 2024-10-28
125 | 126 | RL_04_ADD_SH_0940 | Body | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-11-06
126 | 127 | RL_04_ADD_SH_0950 | Body | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-10-29
127 | 128 | RL_04_ADD_SH_0960 | Body | Approved |  |  | Sunny Walunj | comp_v004 | 2024-10-10 | 2024-11-06
128 | 129 | RL_04_ADD_SH_0970 | Body | Approved |  |  | Sunny Walunj | comp_v002 | 2024-10-10 | 2024-11-06
129 | 130 | RL_04_ADD_SH_1150 | Body | Approved |  |  | Vivek Mahajan | comp_v005 | 2024-10-10 | 2024-10-27
130 | 131 | RL_04_ADD_SH_1160 | Body | Approved |  |  | Vivek Mahajan | comp_v004 | 2024-10-10 | 2024-10-27
131 | 132 | RL_04_ADD_SH_1170 | Body | Approved |  |  | Vivek Mahajan | comp_v007 | 2024-10-10 | 2024-11-06
132 | 133 | RL_04_ADD_SH_1200 | Hand | Approved |  |  | Vivek Mahajan | comp_v002 | 2024-10-10 | 2024-10-28
133 | 134 | RL_04_ADD_SH_1240 | Hand | Approved |  |  | Vivek Mahajan | comp_v002 | 2024-10-10 | 2024-11-06
134 | 135 | RL_04_ADD_SH_1260 | Hand | Approved |  |  | Vivek Mahajan | comp_v004 | 2024-10-10 | 2024-11-06
135 | 136 | RL_04_ADD_SH_1270 | Hand | Approved |  |  | Vivek Mahajan | comp_v005 | 2024-10-10 | 2024-10-28
136 | 137 | RL_04_ADD_SH_1290 | Hand | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-10-28
137 | 138 | RL_04_ADD_SH_1350 | Hand | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-10-29
138 | 139 | RL_04_ADD_SH_1380 | Hand | Approved |  |  | Vivek Mahajan | comp_v004 | 2024-10-10 | 2024-10-29
139 | 140 | RL_04_ADD_SH_1420 | Hand | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-11-06
140 | 141 | RL_04_ADD_SH_1440 | Hand | Approved |  |  | Vivek Mahajan | comp_v004 | 2024-10-10 | 2024-10-29
141 | 142 | RL_04_ADD_SH_1480 | Hand | Approved |  |  | Vivek Mahajan | comp_v004 | 2024-10-10 | 2024-11-06
142 | 143 | RL_04_ADD_SH_1500 | Hand | Approved |  |  | Vivek Mahajan | comp_v002 | 2024-10-10 | 2024-11-06
143 | 144 | RL_04_ADD_SH_1540 | Hand | Approved |  |  | Vivek Mahajan | comp_v004 | 2024-10-10 | 2024-11-06
144 | 145 | RL_04_ADD_SH_1560 | Hand | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-11-06
145 | 146 | RL_04_ADD_SH_1580 | Hand | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-11-06
146 | 147 | RL_04_ADD_SH_1590 | Hand | Approved |  |  | Vivek Mahajan | comp_v005 | 2024-10-10 | 2024-11-06
147 | 148 | RL_04_ADD_SH_1610 | Hand | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-11-06
148 | 149 | RL_04_SH_0180 | Need to render comp version after replacing prep | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-25
149 | 150 | RL_04_SH_0190 | Body | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-25
150 | 151 | RL_04_SH_0200 | Need to render comp version after replacing prep | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-25
151 | 152 | RL_04_SH_0210 | Need to render comp version after replacing prep | Approved |  |  | Nikhil Shivshive | comp_v003 | 2024-10-10 | 2024-10-25
152 | 153 | RL_04_SH_0220 | Need to render comp version after replacing prep | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-25
153 | 154 | RL_04_SH_0230 | Need to render comp version after replacing prep | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-25
154 | 155 | RL_04_SH_0280 | Need to render again with the updated prep version | Approved |  |  | Vivek Mahajan | comp_v003 | 2024-10-10 | 2024-10-24
155 | 156 | RL_04_SH_0480 | Body | Approved |  |  | Shraddha Anawat | comp_v009 | 2024-10-10 | 2024-10-25
156 | 157 | RL_04_SH_0490 | Body | Approved |  |  | Shraddha Anawat | comp_v003 | 2024-10-10 | 2024-10-25
157 | 158 | RL_04_SH_0500 | Body | Approved |  |  | Shraddha Anawat | comp_v005 | 2024-10-10 | 2024-10-25
158 | 159 | RL_04_SH_0510 | Body | Approved |  |  | Shraddha Anawat | comp_v006 | 2024-10-10 | 2024-10-25
159 | 160 | RL_04_SH_0690 | Body | Approved |  |  | Vivek Mahajan | comp_v006 | 2024-10-10 | 2024-11-06
160 | 161 | RL_04_SH_0710 | Body | Approved |  |  | Vivek Mahajan | comp_v005 | 2024-10-10 | 2024-11-06
161 | 162 | RL_04_SH_0820 | Face & Body | Approved |  |  | Vivek Mahajan | comp_v002 | 2024-10-10 | 2024-10-28
162 | 163 | RL_04_SH_0840 | Face & Body | Approved |  |  | Vivek Mahajan | comp_v002 | 2024-10-10 | 2024-10-28
163 | 164 | RL_05_ADD_SH_0120 | Under eyes | Approved |  |  | Kiran Lachure | comp_v002 | 2024-10-10 | 2024-10-25
164 | 165 | RL_05_ADD_SH_0140 | Hand | Approved |  |  | Kiran Lachure | comp_v002 | 2024-10-10 | 2024-10-24
165 | 166 | RL_05_ADD_SH_0200 | Makeup & Chest | Approved |  |  | Kiran Lachure | comp_v003 | 2024-10-10 | 2024-10-25
166 | 167 | RL_05_ADD_SH_0240 | Sharp Forhead and Remove Wrinkles | Approved |  |  | Kiran Lachure | comp_v003 | 2024-10-10 | 2024-10-25
167 | 168 | RL_05_ADD_SH_0260 | Neck Wrinkles | Approved |  |  | Kiran Lachure | comp_002 | 2024-10-10 | 2024-10-26
168 | 169 | RL_05_ADD_SH_0280 | Neck Wrinkles | Approved |  |  | Kiran Lachure | comp_v002 | 2024-10-10 | 2024-10-26
169 | 170 | RL_05_ADD_SH_0290 | Neck Wrinkles | Approved |  |  | Kiran Lachure | comp_v002 | 2024-10-10 | 2024-10-26
170 | 171 | RL_05_ADD_SH_0400 | Legs | Approved |  |  | Kiran Lachure | comp_v005 | 2024-10-10 | 2024-10-27
171 | 172 | RL_05_ADD_SH_0420 | Reduce Chest | Approved |  |  | Kiran Lachure | comp_v002 | 2024-10-10 | 2024-10-27
172 | 173 | RL_05_ADD_SH_0510 | Legs | Approved |  |  | Kiran Lachure | comp_v002 | 2024-10-10 | 2024-10-26
173 | 174 | RL_05_ADD_SH_0550 | Face & blackspot | Approved |  |  | Kiran Lachure | comp_v003 | 2024-10-10 | 2024-10-27
174 | 175 | RL_05_ADD_SH_0660 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-27
175 | 176 | RL_05_ADD_SH_0700 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-27
176 | 177 | RL_05_ADD_SH_0740 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-27
177 | 178 | RL_05_ADD_SH_0820 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-27
178 | 179 | RL_05_ADD_SH_0840 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-27
179 | 180 | RL_05_ADD_SH_0860 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-27
180 | 181 | RL_05_ADD_SH_0880 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-27
181 | 182 | RL_05_ADD_SH_0900 | Neck Wrinkles | Approved |  |  | Nikhil Shivshive | comp_v002 | 2024-10-10 | 2024-10-27