## Sheet1
# | SHOT_NUMBER | TASK | STATUS | THUMBNAIL | DEPARTMENT | ARTIST | START DATE | ETA | NOTES
1 | RL_03_SH_0080 | Replace the banner text | WIP | ..\thumbails\base64.txt | Compostiting | Darshan Borde | 21/11/2024 16:30 | 21/11/2024 16:30 | The font of the text on banner needs to be changed.
2 | RL_01_SH_0130 | Add muzzle flashes to the gun | APP | ..\thumbails\02.png | Prep | Tanmay Maheshwari | 21/11/2024 16:30 | 24/12/2024 12:30
3 | RL_06_SH_0040 | Remove the Tree in the Bg | APP | ..\thumbails\03.png | Compositing | Krishna Jejukar | 21/11/2024 16:30 | 21/11/2024 16:30
4 | RL_05_SH_200 | Add the Flash effect to the character while he is running | NA | ..\thumbails\04.png | Prep | Kaka | 21/11/2024 16:30 | 21/11/2024 16:30 | The flash effect should match in the sequence
5 | RL_03_SH_0260 | Add Magical Effect to the spark | WIP | ..\thumbails\05.png | Compositing | Rohit Chavan | 21/11/2024 16:30 | 21/11/2024 16:30 | Brightness of spark should be reduce to 50%
6 | RL_01_SH_0243 | Face Cleanup | OMIT | ..\thumbails\06.png | Animation | Tanmay Maheshwari | 21/11/2024 16:30 | 31/01/2025 16:30
7 | RL_02_SH_0190 | Replace the prop wall to CG wall | NA | ..\thumbails\07.png | Rotocopy | Rohit Chavan | 21/11/2024 16:30 | 21/11/2024 16:30 | Roto all characters
8 | RL_03_SH_0869B | Remove the wire and the Rig | WIP | ..\thumbails\08.png | Compositing | Yadeb Btala | 21/11/2024/ 16:30 | 2025-02-02 06:30